## Roadmap
Sheet description | This sheet will be used to track all the planned features that cohere are worknig on and their expected release | Current core version: |  | v0.0.0 | Next version expected release: | v0.31.2 (unknown)
Release Notes: | https://private.docs.cohere.com/north/changelog
Feature Name | Details | Expected Version | Notes | Business Capabilities | Technical Capabilities
Enhance Chat/Agents Interface | Home composer cleanup: a single entry point for knowledge workTools retain between user conversations | v0.31.2
Document Creation | Ability to trigger document creation through chat - Canvas experience for Document Creation - Ability to export documents into docx and google drive | v0.31.2
North Tables | Ability to populate a table of information using LLMs calls with parameters housed in columns (i.e. a column named “company name” ) | v0.31.2
Improved White-Labeling Support | Customization of fonts, icons, animations | v0.31.2
North Admin - Product Analytics | Ability to view high-level metrics of North adoption within your organization (e.g. number active users, total messages sent, total documents created, total automations run) | v0.31.2 | - total automations run and total documents created are not covered in this version but we have added total input and output tokens consumed on a daily basis
North Logging & Monitoring | Robust error logging through North - Audit logs available in North - Standardized prometheus metrics and logs - Improved health metrics page | v0.31.2 | - audit logs are avaliable for admin actions but not for North in this version - there are no longer plans to improve the health metrics page in the admin panel aside from what is currently available
Automations / Workflows V2 - POC | Support the ability to specify model per node in an automation - Support for Conditionals, MCP, Complex Expressions, and early termination nodes - Ability to test the entire workflow - Automations creation compatible with RBAC and running individual automations are also gated via RBAC | v0.31.2 | - Ability to test the entire workflow within the automation builder is slated for v1.2.0
Chat/Agents Interface | - Action taking tools through chat - Ability to create simple automations through chat and schedule them in chat | v1.0.0 | - ability to create simple automations through chat and schedule them is slated for v1.4.0 - Being able to schedule an automation will happen before scheduling an automation created through chat
Document Creation v2 | Start from draft notes - One-click shortcuts for document improvements (e.g. “make it shorter”) - Ability to create a document based off an example (for style / structure) - Improved document sharing | v.1.2.0+2 | - One-click shortcuts for document improvements (e.g. “make it shorter”) is scheduled for v1.2.0 - Ability to create a document based off an example is scheduled for v1.4.0
North Tables v2: | Ability to trigger table creation through chat - Support import from CSV and export to CSV - Ability to share tables | v1.1.0 + 2 | - Ability to trigger table creation through chat is scheduled in v1.1.0 / v1.2.0 depending on the internal evaluations - Ability to share tables has been scoped to just public sharing - Export a table to CSV is supported in v1.0.0 but import from CSV is currently not scoped
Deep Research v1 | Ability to launch deep research using websearch - Ability to create a deep research based off an example (for style / structure) | v1.4.0
Agent Builder v1 | Interactive experience to build/test/improve custom agents (instructions, tools, data sources, etc.) | v1.6.0 | - We are planning to move this up but have yet to confirm engineering and design resources
North Admin | LLM Traces offered for features of North (e.g. Document Creation, Automations, Custom Agents) for auditing, analysis, and optimization - Implicit global priority queue for real time traffic over batched workloads - Integrate with 3rd party Agents | v1.4.0 + 2 | - implicit global priority queue is scheduled for v1.4.0 - LLM traces will be released on a rolling basis for each features - integration with 3rd party Agents is currently de-prioritized until later Q4
Automations / Workflows V2 - Pilot | Local File support for File Input into an Automation - Public URL support, Raw HTTP request, and MCP only Nodes - Looping, and support for Retries in a Node - Local versioning - Testing a subset of an automation - Ability to schedule an automation | v.1.4.0+2 | - Local file support scheduled for v1.4.0 - Various nodes will be released from v1.2.0 to v.1.4.0 - Looping and support for retries in a node is scheduled for v1.4.0 - Local versioning is scheduled for v1.5.0/v1.6.0 - Testing a subset of an automation is scheduled for v1.5.0 - Ability to schedule an automation is scheduled for v1.4.0
Chat/Agents Interface | Ability to chat with a citation (e.g. if the quoted citation comes from a datasource, you are able to thread a chat within it) | v1.6.0 | - This feature is dependent on user-demand
Deep Research v2 | Ability to launch deep research using 1st party tools and MCP tools | v1.6.0
WorkSpaces v1: | Organizational feature to link agents, files, chat, tables, automations, and created assets (e.g. tables and documents) for managing long-term work | v1.6.0
Admin Safety Guardrails: | Implementation of security, bias prevention, and ethical AI safeguards to support responsible AI usage | v1.6.0
Admin Agent/Automation Cost Controls | Admins are able to set the cost controls attached to users, groups, agents and automations (both 1st party and 3rd party agents and models) | v1.4.0
Automations / Workflows V2 - V2 Beta | Input from 1st Party file-storage systems as input - Ability to add date time, date range as inputs - Ability to add authenticated URL as an input - Ability for human in the loop node - Ability for an automation as a sub-process within another automation - GitOps management for Automations - Outputs of automations are mutable in chat | v1.5.0
Mobile version of North | iOS native application for North, running off your internal instance | Not Scoped Currrently for FY2025